The Organic Pet Commerce Engine

A zero-media-spend blueprint for taking a personalised pet accessories Shopify store towards $10,000 in 30 days

Direct answer

No organic growth system can honestly be guaranteed to produce $10,000 in 30 days. Distribution is probabilistic, a new store has no baseline, and weak products, fulfilment or unit economics cannot be rescued by content volume alone.

This corpus is designed to be failure-resistant instead. It turns the target into measurable requirements, makes TikTok, Instagram Reels, YouTube Shorts, Pinterest, Facebook Reels, Google free listings, SEO and email work as one system, and gives an agent team explicit production, approval, measurement and correction loops. The operating principle is simple:

One hero product. Three original master videos per day. Native packaging for every viable surface. Every post tagged to revenue. Every winner multiplied. Every leak repaired within 24 hours.

The strongest counterpoint is that 30 days is an aggressive validation window, not a reliable time horizon for compounding organic growth. The engine should therefore optimise first for proof of a repeatable content-to-order path, while still pursuing the full revenue target.

Operating assumptions

The blueprint uses these defaults because no store baseline was supplied:

- Market: UK first, with the $10,000 target held as the reporting target in Shopify.

- Starting point: new or low-traffic store with no dependable audience.

- Offer: one visually demonstrable personalised pet accessory, plus two relevant add-ons.

- Average order value target: $40 or more.

- Gross margin target: 60% or more before team costs.

- Assets: products, pets and real human hands or creators are available.

- Media spend: zero. Shopify fees, product costs, fulfilment, software and team time are not free.

- Publishing: agents prepare drafts, but a human approval gate controls every post, send, offer and public reply.

- Creative rule: real product footage is the source of truth. AI can research, script, edit, caption, classify and analyse, but it must not fabricate product performance, customer reactions or reviews.

The category has real demand. US pet-industry expenditure reached $158 billion in 2025, while UK research reports that 61% of owners prioritise their pets’ needs above their own and that owners increasingly buy products reflecting their personal preferences.[1][2] This supports an emotional, identity-led proposition, but it does not prove demand for any particular SKU.

The target equation

The target must be managed as a commercial equation rather than a view target:

Revenue = qualified sessions × store conversion rate × average order value

| Scenario | AOV | Store conversion | Orders needed | Sessions needed | Sessions per day |
| --- | --- | --- | --- | --- | --- |
| Hard mode | $25 | 1.5% | 400 | 26,667 | 889 |
| Base plan | $40 | 2.0% | 250 | 12,500 | 417 |
| Strong offer | $60 | 2.5% | 167 | 6,680 | 223 |

These are planning scenarios, not industry benchmarks. At the base plan, 250 orders means roughly 8 to 9 orders per day. If 1% of qualified content views become Shopify sessions, the engine needs about 1.25 million qualified views during the month. At a 2% view-to-session rate, it needs about 625,000.

This is why the engine must raise AOV and conversion rather than chase views alone. A bundle that raises AOV from $25 to $40 cuts the required order count by 150. A store converting at 2% needs half as many sessions as one converting at 1%.

Non-negotiable gates

Do not begin the 30-day publishing sprint until all eight gates pass.

| Gate | Pass condition | Failure action |
| --- | --- | --- |
| Product | A stranger understands the product and personalisation in 3 seconds | Reshoot the reveal and simplify the offer |
| Margin | Contribution margin is known for every hero SKU and bundle | Fix price, COGS, packaging or shipping |
| Fulfilment | Production capacity exceeds the daily order target | Cap orders or extend the target window |
| Delivery | A credible production and arrival estimate appears before checkout | Add dated delivery guidance |
| Personalisation | Required fields, limits, preview and spelling confirmation work on mobile | Stop traffic until repaired |
| Trust | Real images, policies, contact details and proof are visible | Build proof before promotion |
| Tracking | Test orders preserve UTM, creative ID and landing-page data | Repair attribution before scale |
| Rights | Every clip, image, voice, pet and music track has usable rights | Quarantine the asset |

The final gate matters because platforms reward original work. Instagram states that eligible original content without visible watermarks can be tested with a small audience and expanded as it performs; duplicate posts may be replaced by the original in recommendations.[3][4] Facebook likewise prioritises content created by the publisher and reduces distribution for duplicated or minimally changed work.[5][6]

The commercial wedge

Choose one hero SKU

Do not market a catalogue. Market a transformation.

Score each candidate product from 1 to 5 on the following dimensions:

- Visual reveal: can the personalisation be understood with no explanation?

- Emotional charge: does it signal identity, belonging, celebration or remembrance?

- Demonstrability: can agents produce 100 genuinely different videos around it?

- Gross margin: does it fund remakes, errors and customer service?

- Fulfilment speed: can it arrive within the promise?

- Error resistance: are spelling, sizing and colour mistakes controllable?

- Shipping simplicity: is it small, durable and inexpensive to send?

- Safety: can materials and use be described accurately?

- Bundle fit: do two natural add-ons raise AOV without confusing the choice?

- Proof potential: will customers want to film the reveal or pet reaction?

The winner becomes the hero for 30 days. Other products remain available, but they do not receive equal creative attention.

Position the transformation

A personalised accessory is not merely an object with a name on it. The strongest positioning territory is:

“The little thing that proves this pet is family.”

Use four buying frames:

| Buyer | Job to be done | Emotional result | Useful content |
| --- | --- | --- | --- |
| Devoted pet parent | Express the pet’s identity | Pride and belonging | Reveals, routines, breed humour, matching styles |
| Gift buyer | Find a gift that feels considered | Relief and social credit | Gift guides, reactions, deadline content |
| New pet household | Mark an arrival or adoption | Celebration and attachment | First collar, name reveal, welcome-home stories |
| Occasion buyer | Make a birthday, gotcha day or Christmas special | Anticipation and memory | Countdown, unboxing, party, stocking content |

A memorial line can be meaningful, but it should be a separate, sensitive lane. Never use grief as shock bait.

Build the offer ladder

Use a three-level offer architecture:

| Level | Purpose | Structure |
| --- | --- | --- |
| Hero | Make the decision simple | One personalised bestseller with clear options |
| Bundle | Raise AOV | Hero plus two genuinely complementary accessories |
| Giftable | Capture intent | Gift packaging, message card or occasion-ready version |

Shopify’s Search & Discovery app can place complementary and related products on product pages, and Shopify recommends products that are useful rather than arbitrary.[^7] Do not use unrelated upsells. They weaken confidence.

Avoid permanent discounting

Use value before price cuts:

- Bundle saving that protects absolute margin.

- Free personalisation if it is normally chargeable.

- Free gift packaging above a threshold.

- A clear shipping threshold.

- A time-bound production slot only when capacity is genuinely limited.

- A first-order code only for captured subscribers, not every visitor.

False urgency and perpetual countdowns destroy trust. Every deadline must map to production capacity, dispatch or a real occasion.

Shopify conversion layer

Organic reach only matters if the store converts. Baymard’s long-running research places average cart abandonment around 70%, and its testing repeatedly finds that checkout design can itself cause abandonment.[8][9] The store is therefore part of the content engine, not a separate project.

Hero product page

The mobile product page should follow this order:

- Product-in-use image or short silent loop.

- One-line outcome: what it is, who it is for and why it matters.

- Price and any honest bundle saving.

- Personalisation fields with examples and character limits.

- Live or representative preview, clearly labelled if exact rendering varies.

- Size, colour and material choices.

- Production time and estimated arrival window.

- Add-to-cart button.

- Three proof points: quality, comfort or durability, and service.

- Real customer images and verified reviews.

- “How it is made” visual sequence.

- Size guide and measurement video.

- Care, safety and material details.

- Personalised-item returns explanation.

- FAQ.

- Complementary products.

Shopify recommends detailed specifications, comparison information, comprehensive descriptions, structured data, sizing, materials and care information to improve product understanding for humans and AI systems.[^10] Shopify themes also include important SEO foundations such as sitemaps and product structured data, although implementation should still be checked.[^11]

Personalisation error control

Use a deliberate confirmation flow:

- Label the field “Name exactly as it should appear”.

- Display the entered text beside the add-to-cart button.

- State capitalisation rules.

- Reject unsupported characters before checkout.

- Require a checkbox: “I have checked spelling, size and colour”.

- Store the choice as a line-item property on the order.

- Include the selected personalisation in cart, checkout and confirmation email.

- Route unusual values to manual review.

Trust block

Show the following near the purchase decision:

- Actual production location.

- Actual dispatch time.

- Tracked or untracked delivery options.

- Materials and safety limitations.

- Contact route.

- Secure payment methods.

- Honest personalised-return rules.

- What happens if the business makes an error.

In the UK, change-of-mind cancellation rights generally do not apply to personalised or custom-made items, but faulty, misdescribed or unfit goods still require an appropriate remedy.[^12] The policy must say this plainly without implying that personalised products have no consumer protection.

Checkout

- Make guest checkout obvious.

- Show total costs before the final step.

- Offer the payment methods the target market expects.

- Remove non-essential fields.

- Explain why any phone number is requested.

- Preserve the personalisation summary.

- Display an estimated arrival date rather than making the buyer calculate it.

- Run a complete mobile test order every week.

Capture and recovery

Shopify Forms is free to install and can collect email, SMS or WhatsApp consent, apply customer tags and trigger automations.[^13] Use one value-led capture:

“Get the pet gift deadline calendar and 10% off your first personalised order.”

Activate these flows:

| Flow | Trigger | Message sequence |
| --- | --- | --- |
| Welcome | New subscriber | Value and code, proof, deadline reminder |
| Browse recovery | Viewed hero product, no cart | Product benefit, FAQ, social proof |
| Cart recovery | Added to cart, no checkout | Personalisation reminder, trust, deadline |
| Checkout recovery | Began checkout, no order | Resume link, shipping and support |
| Post-purchase | Order placed | Confirmation, production story, care |
| Review and UGC | Delivered | Honest review request, then optional content invitation |
| Repeat or gift | Relevant interval | Occasion prompt or complementary product |

Shopify provides pre-built welcome, browse, cart and checkout automations, and abandoned-checkout emails do not count towards the monthly Shopify Messaging email limit.[14][15] Do not activate duplicate automations targeting the same behaviour.

Measurement architecture

One commercial source of truth

Shopify is the revenue ledger. The content database is the creative ledger. Platform analytics explain attention, but they never override paid-order data.

Shopify marketing reports can group performance by UTM source, medium and campaign, compare attribution models, and show sessions, orders, sales and conversion by channel.[^16] Shopify changed session measurement in September 2026, including bot filtering and session handling, so comparisons crossing that rollout need caution.[17][18]

UTM standard

Every external link uses:

utm_source={tiktok|instagram|youtube|pinterest|facebook|google}
utm_medium={organic_social|organic_video|organic_search|product_listing}
utm_campaign=pet_10k_30d_{yyyymm}
utm_content={creative_id}_{hook_id}_{variant}

Example:

/products/hero?utm_source=tiktok&utm_medium=organic_video&utm_campaign=pet_10k_30d_202610&utm_content=TT_E03_H07_A

Use a clean redirect or link-in-bio page only if it preserves parameters and does not add unnecessary clicks.

Creative ID

Use this naming pattern:

{platform}_{pillar}_{format}_{concept}_{hook}_{version}_{date}

Example:

TT_EMO_REVEAL_C03_H07_V2_20261018

Content record

Each creative needs these fields:

creative_id:
        
      parent_concept_id:
        
      product_id:
        
      audience:
        
      buyer_stage:
        
      pillar:
        
      format:
        
      hook_text:
        
      promise:
        
      proof:
        
      cta:
        
      search_phrase:
        
      source_assets:
        
      rights_status:
        
      platform:
        
      caption:
        
      cover_text:
        
      landing_url:
        
      utm_content:
        
      approval_status:
        
      published_url:
        
      published_at:
        
      metrics_2h:
        
      metrics_24h:
        
      metrics_72h:
        
      metrics_7d:
        
      sessions:
        
      add_to_carts:
        
      checkouts:
        
      orders:
        
      revenue:
        
      learning:
        
      next_action:

Metric hierarchy

Judge content in this order:

- Contribution margin attributed to the creative.

- Revenue per 1,000 views.

- Orders per 1,000 views.

- Shopify sessions per 1,000 views.

- Product-page add-to-cart rate.

- Profile visits and link clicks per 1,000 views.

- Shares and saves per 1,000 views.

- Completion, average watch time and viewed-versus-skipped behaviour.

- Likes and follower count.

Likes are a weak business outcome. A 5,000-view video producing five orders is more valuable than a 500,000-view video producing none.

Funnel diagnosis

| Pattern | Likely issue | Next test |
| --- | --- | --- |
| Low views, strong conversion | Packaging or hook | Keep the offer, create 10 new openings |
| High views, low profile visits | Entertainment without product curiosity | Show product sooner and sharpen intrigue |
| High profile visits, low sessions | Bio or CTA friction | Rewrite bio, simplify link destination |
| High sessions, low add-to-cart | Product page, price or trust | Add proof, clarify delivery, test offer |
| High add-to-cart, low checkout | Shipping surprise or personalisation friction | Show full costs and simplify fields |
| High checkout, low purchase | Payment, technical or trust issue | Run test orders and payment review |
| Orders, low margin | Bad economics | Raise AOV, price or reduce fulfilment cost |
| Sales spike, fulfilment delay | Capacity failure | Cap volume and update delivery promise |

Content strategy

The content promise

The account should be useful or enjoyable even when the viewer does not buy. Its editorial proposition is:

Personalised ways to celebrate the animals who run the household.

This opens a much larger creative world than repeatedly filming a product on a table.

Pillar mix

| Pillar | Share | Purpose | Examples |
| --- | --- | --- | --- |
| Emotion and identity | 30% | Shares and desire | Name reveals, pet-parent moments, gotcha days |
| Entertainment | 20% | Reach | Pet POV, breed humour, household roles |
| Utility and search | 20% | Evergreen discovery | Sizing, materials, gift guides, care |
| Proof and process | 20% | Trust and conversion | Making, packing, durability, reviews |
| Offer and urgency | 10% | Immediate action | Bundles, order deadlines, availability |

The product should appear naturally in most posts, but only 10% should feel like a conventional promotion.

Creative grammar

Every short video follows five beats:

- Stop: a visual or verbal pattern break in the first frame.

- Orient: make the pet, problem or occasion obvious.

- Reward: deliver humour, emotion, utility or surprise.

- Prove: show the real product, process or result.

- Move: ask for one next action.

TikTok’s official creative guidance uses a similar hook, body and close structure, identifies the first 3 to 6 seconds as crucial, recommends full-screen 9:16 footage, sound and a clear CTA, and favours native, less polished execution.[19][20][^21] These are useful production principles, not a promise of organic reach.

Format bank

Use these repeatable shows:

- Name Reveal of the Day.

- Pack an Order With Me.

- Pet CEO Performance Review.

- What Your Pet’s Accessory Says About You.

- Three Gifts for the Person Who Calls Their Dog Their Child.

- Before and After Personalisation.

- Customer Brief to Finished Product.

- Most Chaotic Pet Names This Week.

- Pet Name Spelling Court.

- Breed Colour Pairing Guide.

- New Puppy Starter Pick.

- Cat Household Gift Guide.

- Gotcha Day Countdown.

- Birthday Order Deadline.

- Christmas Stocking Test.

- Material Close-Up and ASMR.

- Durability Demonstration.

- Size This Pet With Me.

- The Mistake This Order Avoided.

- One-Star Fear, Five-Star Proof.

- Things Pet Parents Understand.

- Pet POV: “They Put My Name on Everything”.

- Matching Pet and Human Aesthetic.

- Comment Chooses Tomorrow’s Design.

- Guess the Pet’s Name.

- Rescue Story With Permission.

- Old Photo to New Keepsake.

- The Order That Made the Team Cry.

- FAQ in 15 Seconds.

- Real-Time Personalisation.

Hook bank

- “If your dog is basically your child, stop scrolling.”

- “This is what arrived after one customer sent us a name.”

- “Three seconds before this became their favourite gift.”

- “Nobody warns new pet parents about this purchase.”

- “The pet name we nearly refused to print.”

- “POV: your pet has better accessories than you.”

- “Do not order a personalised collar before checking this.”

- “The easiest way to get pet sizing wrong.”

- “We made today’s order for a dog called…”

- “A £30 gift should not feel this personal.”

- “This is your sign to celebrate their gotcha day.”

- “For the person whose camera roll is 98% dog.”

- “Watch a blank accessory become theirs.”

- “Which colour belongs to a golden retriever?”

- “The spelling check that saved this order.”

- “Pet parents will understand why this matters.”

- “We tested whether the name survives real life.”

- “The gift for someone who says they need nothing.”

- “Things in our order queue that sound made up.”

- “Your cat would never admit they love this.”

- “What $40 buys a very important family member.”

- “We turned this customer comment into a product.”

- “One order, four tiny decisions, zero room for error.”

- “The reveal is at the end, but the name is outrageous.”

- “Before you buy a pet gift, answer this.”

- “This colour combination should not work, but it does.”

- “The personalised gift deadline nobody remembers.”

- “A small business order from start to finish.”

- “This is why the preview matters.”

- “Send this to the person who throws their dog a birthday.”

CTA bank

Use one CTA, matched to the viewer’s stage:

| Intent | CTA |
| --- | --- |
| Conversation | “What would yours say?” |
| Share | “Send this to the pet parent in your life.” |
| Save | “Save this before you measure.” |
| Follow | “Follow for tomorrow’s name reveal.” |
| Search | “Search ‘personalised pet gift’ and compare the details.” |
| Visit | “Build yours through the link in the profile.” |
| Buy | “Order by the displayed cutoff for the current arrival window.” |
| Proof | “See the full making process on the product page.” |

Script templates

Reveal

0:00  Extreme close-up of blank product.
VO: “This started with one name.”
0:02  Fast making sequence.
Text: “Spelling checked twice.”
0:07  Finished reveal on pet.
VO: “Now it could only belong to Mabel.”
0:11  Reaction or movement.
CTA: “What name should be next?”

Gift buyer

0:00  Gift box in hand.
VO: “For the person who says they need nothing…”
0:03  Open to personalised accessory.
VO: “…but has 14,000 photos of their dog.”
0:08  Detail and packaging.
Text: “Made with their pet’s name.”
0:12  Delivery guidance.
CTA: “Check the current order deadline in the profile.”

Search utility

0:00  Show two sizes on screen.
Text: “How to size a personalised pet accessory.”
0:02  Demonstrate measurement.
0:08  Show common mistake.
0:12  Show correct fit.
CTA: “Save this, then use the full guide on the product page.”

Objection

0:00  On-screen comment: “What if I spell it wrong?”
0:02  Show input, cart and confirmation.
VO: “The exact text follows the order through all three steps.”
0:09  Show manual review flag.
CTA: “Check it once here, once in cart, and once in your email.”

Process

0:00  Finished product first.
Text: “From order to dispatch.”
0:01  Order card, safe personal data hidden.
0:04  Personalisation.
0:08  Quality check.
0:11  Packing.
0:14  Dispatch label, address hidden.
CTA: “Tomorrow’s order could be yours.”

Humour

0:00  Pet looking demanding.
Text: “POV: the household CEO checks the new uniform.”
0:03  Accessory reveal.
0:07  Pet walks away.
Text: “Approved. No feedback provided.”
CTA: “Tag your own difficult executive.”

Platform playbooks

TikTok

Role

TikTok is the fastest testing surface. Use it for discovery, search-led utility, comment mining and rapid creative iteration.

TikTok Creator Search Insights exposes frequently searched topics, content gaps, related searches and post search performance.[^22] TikTok says its search recommendations consider query match, hashtags, sounds, watch completion, skips and other interaction signals.[^23]

Cadence

- Three original posts per day.

- One search-led utility video.

- One emotional or entertaining video.

- One proof, process or offer video.

- Two comment-reply videos per week, more when a thread contains real demand.

- One live session per week only after the store and fulfilment gates pass.

Packaging

- 9:16, at least 720p, well lit.

- Product or pet in the first frame.

- Spoken search phrase, on-screen phrase and natural caption alignment.

- Clear audio, captions and licensed commercial music where needed.

- No imported watermark.

- Use 2 to 5 specific hashtags for classification, not a cloud of generic tags.

- Put the primary search phrase in the caption’s first sentence.

Search clusters

- personalised dog collar

- personalised cat collar

- personalised pet gift

- dog birthday gift

- gotcha day gift

- new puppy gift

- pet Christmas gift

- dog mum gift

- how to measure dog collar

- best collar colour for breed

- custom pet accessory

- gift for pet owner

Validate terms weekly inside Creator Search Insights. Do not assume a phrase is active because it sounds plausible.

Daily research loop

- Pull 20 relevant Creator Search Insights topics.

- Flag content gaps.

- Review TikTok Creative Center for current formats and hashtags. Creative Center is a free public resource containing trends, high-performing examples and creative tools.[24][25]

- Read comments on the brand’s five best and five weakest posts.

- Turn repeated questions, objections and jokes into briefs.

- Store the source and date with every idea.

Instagram

Role

Instagram is the trust, sharing and relationship layer. Use Reels for discovery, carousels for saved utility, Stories for proof and urgency, and Highlights for persistent buying information.

Instagram says engagement per viewer, including watch time, sharing, follows, comments, likes and profile visits, informs distribution; it also encourages an interesting opening and original high-resolution content.[^26] Average and total watch time are available to diagnose where hooks or pacing lose viewers.[^27]

Cadence

- Two Reels per day, natively rendered from the three daily concepts.

- Three to eight Story frames per day.

- Two utility carousels per week.

- One customer or collaborator post per week when rights and disclosure are correct.

- One Trial Reel per day for riskier formats if the feature is available.

Meta reports that Trial Reels first expose a Reel to non-followers; in its internal analysis, many creators who posted more after trying the feature also saw greater non-follower reach, though Meta explicitly says performance is not guaranteed.[^28]

Reels packaging

- Upload a clean master without another platform’s watermark.

- Change the opening frame, caption and audio rather than cloning TikTok blindly.

- Use a cover with 3 to 6 readable words.

- Optimise for sends and saves where the concept supports them.

- Test short direct-response cuts and 30 to 90 second stories. Instagram identifies 30 to 90 seconds as a useful engagement range for recommended Reels, but the message should determine length.[^26]

Story sequence

Frame 1: Poll or question about a pet name, colour or occasion.
Frame 2: Real making or packing clip.
Frame 3: Customer proof.
Frame 4: Product choice or FAQ.
Frame 5: Honest deadline and link sticker.

Highlights

- Start Here

- Bestsellers

- Size Guide

- Reviews

- Making

- Delivery

- Gifts

- FAQ

YouTube Shorts

Role

YouTube Shorts is the evergreen video-search and long-tail discovery layer. It can continue surfacing useful videos after a trend has disappeared elsewhere.

YouTube says Shorts are ranked using viewer personalisation and performance signals such as chose-to-view behaviour, average view duration, average percentage viewed, likes and post-watch surveys.[29][30] Search also considers how metadata matches the query and whether viewers click and watch.[^29]

Cadence

- Two Shorts per day from the best daily concepts.

- One searchable title per Short.

- One weekly compilation or 2 to 5 minute guide built from proven Shorts.

- Link related videos or playlists where available.

Packaging

- Use titles that complete a search, such as “How to Measure Your Dog for a Personalised Collar”.

- Put the answer early.

- Use recurring series and consistent characters.

- Review “viewed versus swiped away”, average view duration and average percentage viewed.

- Do not delete a slow starter merely because TikTok performed faster.

Pinterest

Role

Pinterest is the visual-search, gift-planning and catalogue layer. It has slower feedback than TikTok but a better fit for evergreen gifting, style, breed and occasion searches.

Pinterest describes itself as a place where people search, save and shop ideas.[^31] A Shopify store can connect through the Pinterest app, claim the website, install conversion tracking and generate Product Pins from the catalogue.[32][33]

Foundation

- Create a Pinterest Business account.

- Connect the Shopify catalogue.

- Claim the domain.

- Confirm product title, description, price, availability and image quality.

- Confirm page-view, add-to-cart and checkout events.

- Apply for merchant verification when eligible.

Boards

- Personalised Dog Accessories

- Personalised Cat Accessories

- Gifts for Dog Mums

- New Puppy Gift Ideas

- Pet Birthday Ideas

- Gotcha Day Ideas

- Christmas Gifts for Pets

- Breed Colour Guides

- Pet Memorial Keepsakes, only if genuinely offered

Cadence

- Five fresh Pins per day.

- Two product Pins.

- Two editorial Pins from video stills, guides or carousels.

- One seasonal or search-led Pin.

- Link each Pin to the most specific relevant page.

Do not upload five near-identical designs. Change the visual, promise and search intent.

Google and SEO

Role

Google captures explicit demand from buyers already searching for a product, occasion, breed or problem.

Eligible Shopify products synced through the Google & YouTube app can appear free across Search, Shopping, Images, Lens and YouTube.[34][35] Google recommends descriptive current product data, high-quality images, search-relevant titles and descriptions, and complete attributes.[^34]

Merchant Centre

- Connect the Google & YouTube Shopify app.

- Opt into free listings.

- Mark genuinely custom products correctly when standard identifiers do not exist.

- Add brand, product type and Google Product Category.

- Supply shipping and return information.

- Fix all disapprovals.

- Keep store and feed price, availability and delivery data aligned.

Google states that combining Product structured data with a Merchant Centre feed maximises eligibility and helps it verify product information.[^36]

Page architecture

Create pages only where distinct intent and useful content exist:

- Personalised pet accessories collection.

- Dog and cat sub-collections.

- Occasion collections.

- Product pages for meaningful variants, not thin duplicates.

- Size and measurement guide.

- Materials and care guide.

- Production and delivery page.

- Personalised returns page.

- Gift deadline page.

Editorial sprint

Publish two strong articles per week:

- Best personalised gifts for dog lovers.

- How to choose the right personalised dog collar size.

- New puppy gift checklist.

- Gotcha day gift and celebration ideas.

- Pet birthday gift guide by budget.

- Best collar colours by coat colour.

- When to order personalised Christmas pet gifts.

- How personalised pet accessories are made.

Each article should answer the query directly, use original product photography, link to a relevant product and contain information that would still be useful without the purchase link.

Facebook Reels

Role

Facebook supplies incremental distribution, particularly for shareable pet stories, gift buyers and older household members. Publish natively from a clean master rather than downloading a watermarked copy.

Meta recommends clear vertical Reels without watermarks, original content and experimentation with duration to improve watch time and qualified views.[^37] Keep captions plain, invite genuine pet stories and place buying links only where the post remains useful.

Cadence

- One to two Reels per day.

- One weekly photo or customer story.

- Cross-post only assets the brand created or has rights to use.

- Respond to comments with approved language and route product questions to the right page.

Channels not prioritised

- Reddit: use for listening and answering genuine questions only. Do not run a link-dropping operation.

- X: useful for brand personality, but weak as the primary visual-commerce engine for this target.

- LinkedIn: irrelevant unless the story is about building the agent-led business itself.

- Snapchat: reconsider only if existing customer data shows a strong audience fit.

- Paid creator seeding: not part of a strict zero-spend plan because product, postage or commission has a cost.

The 30-day publishing machine

Output target

Produce three original master concepts per day, then package them natively:

| Daily asset | TikTok | Instagram | YouTube | Facebook | Pinterest |
| --- | --- | --- | --- | --- | --- |
| Search utility | 1 | 1 | 1 | Optional | 2 Pins |
| Emotion or entertainment | 1 | 1 | 1 | 1 | 1 Pin |
| Proof, process or offer | 1 | Trial or Story/Reel | Optional | 1 | 2 Pins |

This yields up to 90 master concepts and roughly 300 to 400 placements in 30 days without pretending that duplicates are new ideas.

Weekly rhythm

| Day | Primary job |
| --- | --- |
| Monday | Search gaps, objections and weekly hypothesis |
| Tuesday | Product proof and process |
| Wednesday | Emotional story and customer evidence |
| Thursday | Utility, comparison and sizing |
| Friday | Humour, trends and community prompts |
| Saturday | Gift use case, unboxing and live session |
| Sunday | Winner review, derivatives and next-week queue |

Day structure

- 08:00: ingest platform, Shopify and comment data.

- 09:00: choose three hypotheses.

- 10:00: scripts, shot lists and asset retrieval.

- 12:00: first cut and rights check.

- 13:00: platform variants.

- 14:00: human approval batch.

- 15:00 onward: approved publishing windows.

- Two hours after each post: packaging check only.

- Next morning: 24-hour performance and funnel review.

- Every 72 hours: winner or loser classification.

Posting time should be learned from account data. It is not a substitute for a strong concept.

Thirty-day sprint

Days 1 to 3: Instrument

- Pick the hero SKU and bundle.

- Calculate contribution margin and daily capacity.

- Repair the mobile product page.

- Complete two mobile test orders.

- Configure UTMs, content IDs and dashboard fields.

- Connect Google, Pinterest and relevant social profiles.

- Activate Forms and non-duplicated recovery flows.

- Build 30 concepts from search, reviews, FAQs and competitor comments.

- Film a reusable product asset library.

Exit condition: a test creative can be traced from platform link to Shopify order.

Days 4 to 7: Establish baseline

- Publish three concepts daily.

- Test three territories: emotion, search utility and process proof.

- Hold product, landing page and offer stable.

- Record 2-hour, 24-hour and 72-hour metrics.

- Interview every customer-service question through the data, not through invented personas.

Exit condition: identify the strongest pillar, format, opening and buyer intent.

Days 8 to 14: Find the wedge

- Allocate 70% of output to the top two territories.

- Make five new hooks for every converting concept.

- Add proof addressing the top three objections.

- Launch the first gift or occasion collection page.

- Publish two search articles.

- Turn the best comments into videos.

Exit condition: at least one creative family produces repeatable Shopify sessions and at least one order path can be attributed.

Days 15 to 21: Multiply winners

For every winner, create:

- A shorter cut.

- A longer story.

- A new first frame.

- A customer or pet variation.

- A search-led version.

- A gift-buyer version.

- A process-proof version.

- A carousel.

- A Pinterest design.

- A product-page module.

Do not merely repost the same file. Preserve the winning mechanism while changing the execution.

Exit condition: more than half of Shopify sessions come from identified creative families rather than unclassified traffic.

Days 22 to 30: Convert demand

- Lead with the best bundle and real deadline.

- Increase Story proof and FAQs.

- Publish customer outcomes with permission.

- Add the strongest objections to the product page.

- Send one approved campaign to consented subscribers.

- Build sequel content around products actually ordered.

- Protect fulfilment capacity.

Exit condition: either the $10,000 target is reached, or the engine produces an evidence-backed diagnosis of the binding constraint and a 30-day correction plan.

Agent operating system

Team topology

| Agent | Owns | Input | Output | Primary KPI |
| --- | --- | --- | --- | --- |
| Orchestrator | Queue and dependencies | Target, capacity, results | Daily plan and exceptions | On-time approved output |
| Demand Scout | Search, trends and comments | Platform tools, reviews | Evidence-backed opportunities | Ideas adopted |
| Voice-of-Customer | Language and objections | Comments, reviews, tickets | Phrase and objection bank | Converting language |
| Offer Strategist | Hero, bundle and CTA | Margin, demand, inventory | Offer briefs | AOV and conversion |
| Concept Agent | Creative hypotheses | Opportunity bank | Concept cards | Concepts reaching test |
| Script Agent | Hooks and scripts | Concept cards | Three script variants | Hook win rate |
| Asset Librarian | Footage and rights | Raw media | Searchable approved assets | Retrieval and rights accuracy |
| Editor | Master videos | Script and assets | Clean masters | QA pass rate |
| Platform Packager | Native variants | Master and platform rules | Captions, covers, versions | Sessions per 1,000 views |
| Compliance Agent | Claims, rights and disclosures | Draft assets | Pass, repair or reject | Zero preventable breaches |
| Publisher | Approval queue | Approved packages | Scheduled draft | Zero unauthorised sends |
| Community Agent | Replies and comment mining | Comments and policy | Draft replies and ideas | Qualified conversations |
| Analyst | Attribution and experiments | Shopify and platform data | Daily decision memo | Revenue per 1,000 views |
| CRO Agent | Store leaks | Funnel and session data | Ranked page tests | Conversion rate |
| Lifecycle Agent | Email and retention | Consent and customer stage | Draft flows and campaigns | Recovered revenue |

Approval wall

Agents may research, calculate, draft, render, check and queue. They must not independently:

- Publish.

- Send email, SMS or direct messages.

- Spend money.

- Offer a refund or exception.

- Change price or shipping promises.

- Delete assets or customer data.

- Change permissions.

- Use a customer’s pet, image, review or story publicly without recorded permission.

The approval card should show:

asset_preview:
        
      platform:
        
      caption:
        
      link:
        
      claim_sources:
        
      rights_status:
        
      disclosure_status:
        
      expected_goal:
        
      risk_flags:
        
      approve_or_reject:

Workflow states

DISCOVERED
BRIEFED
SCRIPTED
ASSET_READY
EDITED
PLATFORM_PACKAGED
COMPLIANCE_PASS
AWAITING_APPROVAL
APPROVED
SCHEDULED
PUBLISHED
MEASURED_2H
MEASURED_24H
MEASURED_72H
SCALED_OR_ARCHIVED

No asset can skip COMPLIANCE_PASS or AWAITING_APPROVAL.

Agent prompt: demand scout

You are the Demand Scout for a personalised pet accessories Shopify store.
Find customer language, active searches, content gaps, objections, occasions and repeatable formats.
Use only dated, traceable evidence from platform search tools, public comments, store data and approved research.
Never invent volume or trend status.
Return:
1. opportunity_id
2. exact phrase
3. source URL or source record
4. source date
5. buyer and stage
6. content gap
7. suggested format
8. product relevance
9. risk
10. confidence: high, medium or low

Agent prompt: concept builder

Create three materially different short-video concepts from the approved opportunity.
Each concept must contain one audience, one promise, one proof and one CTA.
The product must appear naturally by second 5 unless the brief explicitly tests a delayed reveal.
Do not fabricate reactions, reviews, urgency, product properties or pet safety claims.
Return a hook, beat sheet, shot list, on-screen text, voiceover, caption, search phrase and success metric.

Agent prompt: platform packager

Adapt the clean master for TikTok, Instagram Reels, YouTube Shorts, Facebook Reels and Pinterest.
Do not add another platform's watermark.
Preserve the claim and product truth, but rewrite the opening frame, metadata, CTA and cover for each platform.
Use only licensed audio options.
Generate the correct UTM link and creative ID.
Return each package separately with safe-zone and rights checks.

Agent prompt: compliance

Audit this asset for factual claims, customer permissions, copyright, music rights, visible private data, ad disclosure, fake urgency, manipulated product appearance, safety statements and personalised-item policy accuracy.
Classify PASS, REPAIR or REJECT.
For REPAIR, quote the exact element and supply the smallest compliant correction.
Never turn an unknown into a claim.

Agent prompt: analyst

Evaluate performance at 24 and 72 hours using Shopify as the revenue source of truth.
Compare against the same platform's rolling 14-day median and the creative's stated objective.
Prioritise contribution margin, revenue per 1,000 views, sessions per 1,000 views and funnel progression.
Return exactly one decision: SCALE, ITERATE, HOLD or KILL.
Name the evidence, binding constraint and next test.
Do not celebrate reach without commercial movement.

Agent prompt: correction loop

Given the failed outcome, identify the earliest stage at which the evidence diverged from expectation.
Separate creative, audience, offer, product page, checkout, tracking and fulfilment causes.
Recommend one smallest high-information test.
State what remains unchanged so the test is interpretable.

Creative production system

Reusable shot library

Capture these once per product and refresh weekly:

- Blank product macro.

- Name entering the personalisation interface.

- Making or engraving.

- Material texture.

- Colour options together.

- Quality inspection.

- Packaging.

- Gift note.

- Product on small, medium and large pets where relevant.

- Measurement process.

- Movement and real use.

- Owner handoff.

- Pet reaction without coercion.

- Dispatch package with private data covered.

- Finished-product turntable.

- Before and after.

Quality checklist

- The first frame makes sense muted.

- The product is visible and accurate.

- The hook matches the actual payoff.

- No dead air before the first information.

- Text stays within interface-safe areas.

- Captions are accurate.

- Audio is clear and licensed.

- Customer and address data are hidden.

- The CTA asks for one action.

- The landing page matches the promise.

- The creative ID and UTM are correct.

- The export is clean and watermark-free.

Originality standard

One shoot can supply multiple platforms, but each post should be a native edition. Change at least three of:

- First frame.

- Hook wording.

- Shot order.

- Duration.

- Voiceover.

- On-screen text.

- Caption.

- Cover.

- Audio.

- CTA.

This protects relevance and gives the experiment real variation. It does not mean adding cosmetic borders to a copied video, which Meta explicitly treats as insufficient originality.[^5]

Experiment engine

Portfolio rule

- 70% proven mechanisms.

- 20% adjacent tests.

- 10% genuinely new formats.

Before the account has a winner, “proven” means evidence from the first seven days, not generic internet advice.

One-variable tests

Prefer tests that hold the rest constant:

- Same body, three hooks.

- Same video, two CTAs.

- Same offer, two landing-page headlines.

- Same hook, two pets.

- Same concept, emotional versus utility framing.

- Same product, parent versus gift-buyer audience.

Never change hook, offer, audience, page and price together and then pretend to know why performance moved.

Winner rule

A creative becomes a winner when it does one of the following:

- Produces attributed contribution margin.

- Produces orders at an acceptable margin.

- Produces Shopify sessions per 1,000 views at least 1.5 times the platform’s rolling 14-day median.

- Produces a strong lower-funnel signal and enough sample to justify a derivative.

The multiplier is an operating rule, not an industry benchmark.

Scale rule

Within 24 hours of confirming a winner:

- Freeze the original.

- Write the mechanism in one sentence.

- Produce five hook variants.

- Produce three audience or occasion variants.

- Convert it into a carousel, Pin and product-page proof unit.

- Update the content calendar so derivatives replace weak scheduled posts.

Kill rule

Kill or archive a creative family after three materially different hooks fail to produce the intended leading indicator, unless the content supplies valuable search traffic or customer education.

Do not kill the product because one edit failed. Do not keep a concept alive because the team likes it.

Community and UGC loop

Comment operations

Classify every useful comment:

- Purchase intent.

- Product question.

- Objection.

- Personalisation idea.

- Pet story.

- Humour prompt.

- Complaint.

- Safety issue.

- Spam or abuse.

Draft replies in the brand voice and escalate price, policy, complaint, safety and refund matters. High-performing questions become public FAQ videos after approval.

Customer-content request

Ask after delivery, not before the buyer has experienced the product:

Has [pet name] tried it yet? If you are happy to share a photo or short clip, reply here. Please tell us whether we may repost it on our website and social channels. An honest review is always welcome, whether positive or critical.

Store the exact permission, permitted channels and expiry. Never infer consent from a tag.

Review integrity

The US FTC prohibits incentives conditioned on positive sentiment and requires material connections to be disclosed clearly.[38][39] In the UK, advertising must be obviously identifiable, and affiliate or controlled gifted content should be disclosed prominently with “Ad” or an equivalent clear label.[40][41][^42]

Therefore:

- Never buy reviews.

- Never generate customer reviews with AI.

- Never suppress genuine negative reviews selectively.

- If offering an incentive for a review where lawful, require honesty rather than positivity and disclose the incentive.

- Put Ad at the beginning of controlled influencer content.

- Treat affiliate links and codes as advertising.

Seasonal growth map

Personalised goods need earlier marketing because production and delivery create a natural cutoff. Build backwards from each occasion:

| Occasion | Content begins | Conversion emphasis |
| --- | --- | --- |
| Pet birthday | Evergreen | 21, 14 and 7 days before date |
| Gotcha day | Evergreen | Story, memory and celebration |
| New puppy or kitten | Evergreen | Checklist and welcome-home bundle |
| Valentine’s Day | Early January | Pet parent affection and gifting |
| Mother’s/Father’s Day | 5 to 7 weeks before | Dog mum, cat dad, family identity |
| Christmas | September discovery, October education | November cutoffs and gift proof |
| Memorial | Evergreen, no urgency tactics | Sensitivity, craftsmanship and support |

For a sprint beginning 14 October 2026, Christmas and year-end gifting are the immediate commercial window. Display the real final-order date only after production and carrier capacity are confirmed.

Daily dashboard

Track one row per day:

| Area | Metrics |
| --- | --- |
| Revenue | Gross sales, discounts, refunds, net sales, contribution margin |
| Orders | Orders, units, bundle share, AOV |
| Funnel | Sessions, product views, add-to-cart, checkout, purchase conversion |
| Acquisition | Sessions and revenue by source, campaign and creative ID |
| Creative | Posts, views, watch time, completion, shares, saves, profile visits |
| Lifecycle | Subscribers, welcome revenue, recovered checkouts, unsubscribes |
| Operations | Orders in queue, capacity utilisation, error rate, dispatch time |
| Customer | Questions, complaints, review volume, UGC permissions |

Daily decision memo

# Daily Growth Decision
        
        
      ## Result
        
      - Revenue:

      - Contribution margin:

      - Orders:

      - AOV:

      - Sessions:

      - Conversion:

        
      ## Winner
        
      - Creative ID:

      - Evidence:

      - Mechanism:

      - Derivatives due:

        
      ## Leak
        
      - Earliest failing stage:

      - Evidence:

      - Correction today:

        
      ## Risk
        
      - Fulfilment:

      - Customer:

      - Compliance:

        
      ## One call
        
      - SCALE / ITERATE / HOLD / KILL:

Weekly review

Answer only these questions:

- Which buyer produced the most contribution margin?

- Which promise produced the most sessions per 1,000 views?

- Which proof removed the largest objection?

- Which format produced the highest share or save rate?

- Which product-page element appears to block purchase?

- Which channel assisted sales that last-click reporting hides?

- Which creative family deserves 10 derivatives?

- Which activity consumed time without moving a leading or lagging metric?

- Can fulfilment safely support next week’s target?

- What single constraint now limits growth?

End with one call and one counterpoint.

Failure modes

| Failure | Why it happens | Prevention |
| --- | --- | --- |
| Content factory sludge | Agents optimise volume without truth or taste | Human creative bar and real footage |
| Viral but valueless | Entertainment has no product bridge | Product curiosity and matched CTA |
| Catalogue confusion | Too many SKUs split learning | One hero for 30 days |
| Fake social proof | AI invents reactions or reviews | Verified evidence only |
| Attribution blindness | Shared bio links hide creative performance | Creative-level UTMs |
| Platform duplication | Same watermarked file everywhere | Clean master and native editions |
| Offer drift | Daily discounts make tests uninterpretable | Stable weekly offer windows |
| Fulfilment collapse | Viral demand exceeds personalisation capacity | Daily cap and live delivery promise |
| Rights breach | Agents scrape pets, music or creator footage | Rights ledger and quarantine |
| Automated reputational harm | Replies or posts leave without judgement | Approval wall |
| Conversion neglect | Team celebrates views while checkout leaks | Daily funnel diagnosis |
| Premature killing | Organic posts mature at different speeds | 24-hour and 72-hour reviews |
| Trend addiction | Brand borrows reach but builds no memory | Recurring shows and ownable formats |
| Search spam | Thin pages target every breed and occasion | Useful, distinct pages only |
| Margin illusion | Revenue ignores refunds and remake costs | Contribution margin ledger |

Minimum viable tool stack

Use native and free options before adding software:

- Shopify Analytics and marketing reports.

- Shopify Search & Discovery.

- Shopify Forms.

- Shopify Messaging and Flow where available.

- Google & YouTube Shopify app and Merchant Centre.

- Pinterest for Shopify.

- TikTok Creator Search Insights and Creative Center.

- Instagram Insights and Trial Reels where available.

- YouTube Studio.

- A database or spreadsheet for creative records.

- Cloud storage for source footage, exports and rights evidence.

Shopify’s native stack can track marketing performance, collect leads, automate welcome and abandonment journeys, and report sales by UTM.[16][14][^43] Add paid tooling only when a measured bottleneck justifies it.

Launch checklist

Commerce

- [ ] Hero SKU selected.

- [ ] Contribution margin calculated.

- [ ] Bundle configured.

- [ ] Capacity and remake allowance documented.

- [ ] Mobile personalisation flow tested.

- [ ] Delivery date visible.

- [ ] Returns language accurate.

- [ ] Guest checkout obvious.

- [ ] Payment methods tested.

- [ ] Two successful mobile test orders completed.

Tracking

- [ ] UTM taxonomy fixed.

- [ ] Creative IDs generated.

- [ ] Platform links tested.

- [ ] Shopify source and order attribution checked.

- [ ] Pinterest and Google conversion/feed connections checked.

- [ ] Dashboard created.

- [ ] Refunds and discounts included in margin reporting.

Creative

- [ ] 30 concepts queued.

- [ ] 100 reusable source clips captured.

- [ ] Rights recorded.

- [ ] Six recurring shows selected.

- [ ] Hook bank loaded.

- [ ] Caption and accessibility checks active.

- [ ] No-watermark export workflow active.

Lifecycle

- [ ] Forms consent copy checked.

- [ ] Welcome series active.

- [ ] Browse, cart and checkout recovery checked.

- [ ] Duplicate automations removed.

- [ ] Post-purchase and review timing tested.

Governance

- [ ] Human approver named.

- [ ] Publishing permissions limited.

- [ ] Claims source field mandatory.

- [ ] Customer-data redaction active.

- [ ] Complaint and safety escalation defined.

- [ ] Deletion, spend and price changes require explicit approval.

The operating doctrine

The engine wins by compressing the distance between evidence and action:

- Search demand becomes a concept the same day.

- A concept becomes three native tests.

- A test becomes attributed Shopify behaviour.

- Behaviour becomes one decision.

- A winner becomes ten derivatives within 24 hours.

- An objection becomes a video, FAQ and product-page improvement.

- An order becomes proof, then permissioned customer content.

- A fulfilment risk becomes a visible capacity or delivery change before it becomes a complaint.

The goal is not to post more than everyone else. It is to learn faster than competitors while preserving truth, margin and customer trust. If the first 30 days do not reach $10,000, the system has only succeeded if it can identify, with evidence, whether the constraint is attention, traffic, offer, conversion, trust, economics or fulfilment, and make the next move obvious.

References

- [U.S. Pet Industry Reaches $158 Billion in 2025, Poised for Continued Growth in 2026](https://americanpetproducts.org/news/u.s.-pet-industry-reaches-158-billion-in-2025-poised-for-continued-growth-in-2026) - U.S. Pet Industry Reaches $158 Billion in 2025, Poised for Continued Growth in 2026

- UK Pet Retailing Market Report 2025-2030 | Mintel - Pet owners are prioritising their pets, with 61% even placing their pets' needs above their own. Pet...

- Helping Creators Find New Audiences | Instagram for Creators - Instagram introduces changes to give smaller creators more equal chances of breaking through to new ...

- Helping Creators Find New Audiences - Previously, in surfaces with recommended content, reels were ranked primarily based on how an accoun...

- Original Content Guidelines on Facebook | Meta Business ... - To get the best distribution, Meta encourages Pages and profiles to post content they originally pro...

- www.facebook.com · business · helpAbout protecting your original content on Instagram | Meta... - To protect and give credit to original content creators, we’ve implemented tools to protect your con...

- Shopify Help Center | Customize product recommendations with ... - Learn how to customize the recommended products sections on your product pages so that they include ...

- E-Commerce Cart & Checkout Usability Research – Baymard

- Reasons for Cart Abandonment – Why 70% of Do So - Baymard - 67% of all e-commerce visitors abandon their shopping cart. Why? That's the question we try to answe...

- Optimizing your store for AI - Learn how to optimize your product pages and store content to improve visibility in AI search result...

- SEO overview - Learn the basics about SEO.

- Accepting returns and giving refunds: the law - Items bought online, by mail or phone Online, mail and telephone order customers have the right to c...

- Shopify Forms app - Use the Shopify Forms app to create a popup or inline form for customer segmentation and lead genera...

- Creating and managing marketing automations in Shopify Messaging - Create and manage marketing automations for email and SMS.

- Shopify Messaging email pricing - However, abandoned checkout automations are always free and don't count towards the monthly limit. Y...

- Marketing reports - Use the Marketing reports to see how effective your marketing campaigns are and to learn about how y...

- Changes to sessions and conversion rate in Shopify ... - Learn why your sessions, conversion rate, and other session-based metrics might be different after a...

- Analytics - The Analytics page displays key sales and activity metrics for your store.

- Creative Codes

- TikTok Creative Made Simple

- TikTok Creative Codes: 6 Principles for Creating Effective ... - The hook grabs attention with a technique like suspense, surprise or emotion. The body conveys your ...

- Creator Search Insights - TikTok Support

- https://support.tiktok.com/en/using-tiktok/explori...

- About Creative Center - Creative Center is a resource where you can discover the latest trends, success stories, and tools t...

- How to use Trends - Trends displays trending hashtags by industry in the Creative Center. Log in to Creative Center. Cli...

- Instagram for Creators: Frequently Asked Questions - We consider the popularity of trends on Reels to determine how to rank and deliver content associate...

- Discover the Hottest Trends and More Updates on Reels - New insights on total watch time and average watch time to help you better understand how your reels...

- Inspiring Creativity That Brings People Together - About Meta - This is based on an internal analysis of over 400,000 creators actively producing reels before and a...

- Search & discovery tips - On YouTube, viewers are matched to the Shorts they are most likely to watch and enjoy. YouTube’s sea...

- Search & discovery tips - Shorts - YouTube Help - On YouTube, viewers are matched to the Shorts they are most likely to watch and enjoy. YouTube’s sea...

- How Pinterest Works | Pinterest Business - Pinterest is like a visual search engine, guiding people to ideas that are just right for them. Lear...

- Set up your merchant profile - As a merchant on Pinterest, you can showcase and promote your products across the platform. Follow t...

- Connect your Shopify store to your account - Your Shopify product feed will be connected to Pinterest; Product Pins will be generated from your S...

- List your products for free on Google - This article is intended for users of the Google & YouTube app on Shopify For eligible shops, produc...

- Show your products for free on Google - Google Merchant Center Help - This article is intended for users of the Google & YouTube app on ShopifyFor eligible stores, produc...

- Intro to Product Structured Data on Google - To provide rich product data to Google Search you can add Product structured data to your web pages,...

- Best Practices for Facebook Content Monetization - Make original content. Creators receive the greatest distribution when they primarily post content t...

- Endorsements, Influencers, and Reviews - One key is to make a good disclosure of your relationship to the brand. This brochure from FTC staff...

- The Consumer Reviews and Testimonials Rule: Questions ... - But remember that failing to disclose incentives could be a violation of the FTC Act. See, e.g., End...

- Recognising ads: Brand-owned and paid social media

- Like, follow and subscribe to our influencer marketing advice - It may seem obvious, but influencers must follow all UK laws, not just the advertising rules. Here a...

- www.asa.org.uk · news · get-yourself-affiliated-withGet yourself affiliated with the rules on affiliate marketing

- help.shopify.com · en · manualShopify Help Center | Marketing automation tools - Learn how you can use Shopify-built marketing automation apps and tools to streamline email and SMS ...